Phase 1:

Order all hardware for server test array

| Phase |  | Description of task | Status |
| --- | --- | --- | --- |
| Start date | Stop Date | BASIC PROJECT START |  |
| 1 – 10/20/14 | 10/20/14 | Site survey of EarthLink COLO | Done |
| 1 – 10/20/14 | 10/28/14 | Receive signed P&S and check for project | Done |
| 1 - 11/05/14 | 11/08/14 | Order all hardware for test server array | Done |
| 1 – 11/08/14 | 12/31/14 | Work with Supplier to get equipment | Working |
| 1 – 11/13/14 | 11/14/14 | Get Debian OS Images | Done |
| 1 – 11/24/14 | 12/31/14 | Start to Receive hardware from supplier | On-Going |
| 1—11/24/14 | 12/03/14 | Develop Configuration plan and implement (See Startup Spread sheet – attached) | On-Going |
| 1 – 12/03/14 | 12/03/14?? | Receive Main Servers and Comtrol Multiplexor Components | Done |
|  |  | BENCH TEST ALL HARDWARE IN LOCAL LAB |  |
| 2 – 12/04/14 | 12/04/14 | Prepare bench and Configure Switches for initial bench testing | DONE |
| 2 – 12/04/14 | 12/15/14 | Bench Test Main Servers in-house Start; Stop; Description; Status. 12/04; 12/04; Unpack and setup Newcastle and gateshead servers on bench Install Monitors, keyboards, Mouse on both servers Configure 2 class C IP’s for Testing servers Newcastle = 71.126.247.219, gateshead = 71.126.247.217; Done. 12/04; 12/05; Install Debian 7.7.0 OS on main servers in basic configuration to test hardware Basic testing, setup webserver tested from external IP; Done. 12/05; 12/05; Load memcheck 4.3 on both servers and run over night to test memory and CPU; Done. 12/06; 12/06; Load Debian 7.7.0 on Newcastle and Gateshead Configure servers on 71.126.247.219 and 217 respectively Configure LVM’s Configure basic partitions boot = 400MB ext2 MP: / BOOT root= 20GB ext4 MP:/ ROOT swap= 9GB MP: / SWAP; Done. 12/06; 12/06; Load basic apps for configuration on both servers apt-get install git emacs xen-tools; Done. 12/06; 12/07; Create test users for Ian, DonS, and DonK. 12/8; 12/10; Troubleshoot the COMTROL connection problem. Make prototype null modem cables so we can configure the TTY connections from Newcastle to gateshead via serial ports; Done. 12//08; 12/13; Test all servers in house. Run Memtst and install Debian 7.7.0 , Install on in-house network and access the internet Tested 18 servers in all.; Done. 12/10; 12/13; Rewire RJ-45 to DB9 adaptors to be null modem cables from the COMTROL 32 port serial patch panel to test server serial ports. Chris made 26 adaptors; Done. 12/13; 12/15; Reconfigure newcastle and gateshead for installation at COLO,; Done. 12/15; 12/19; Install newcastel and gateshead, PDU’s Switches, and COMTROL serial multiplexors. We installed 6 servers in all, 2 main servers and 2 test servers. After conversation with Ian and Lars we discovered that we have to reconfigure the servers in the rack. Electrically everything on newcastel is working fine, the serial connections work on newcastle but not on gateshead. At this time we believe that it is software related. The main servers have access to the outside world and can be accessed over the internet.; Done. 12/20; 01/05; Reconfigure the existing installed servers, and install the rest of the test servers. Test and install the remaining servers that have yet to be delivered.. |  |
| 2 – 12/05/14 | 01/05/15 | Download Developed Software and configuration files for Server Setup | On-going |
| 2 – 12/10/14 | 12/31/14 | Bench test TESTING servers (24) as they come in, move to COLO as needed | DONE |
| 2 – 12/10/14 | 01/05/15 | Load OS and VM configuration files | DONE |
| 2 – 12/10/14 | 01/10/15 | Bench test both configured main servers | DONE |
|  |  | CONFIGURATION TESTING |  |
| 2 – 12/08/14 | 12/10/14 | Configure COMTROL serial multiplexors and test | DONE |
| 2 – 12/08/14 | 12/10/14 | Configure HP 8 and 48 port switches for COLO operation | DONE |
| 2 – 12/08/14 | 12/10/14 | Configure APC PDU’s and test | DONE |
| 2 – 12/09/14 | 12/31/14 | Install 1or more Set of Test Servers and Run a test trial |  |
|  |  | INSTALL HARDWARE AT COLO (Allow for Christmas Holiday) |  |
| 3 – 12/15/14 | 12/15/14 | Move and Install PDU’s to COLO | DONE |
| 3 - 12/15/14 | 12/15/14 | Move and install network switches to COLO | DONE |
| 3 – 12/15/14 | 12/15/14 | Move tested main servers to COLO and Install | DONE |
| 3 – 12/15/14 | 12/15/14 | Move and test one set of TESTING servers to COLO | DONE |
| 3 – 12/17/14 | 12/22/14 | Move more test serfvers to COLO |  |
|  |  | ACCEPTANCE TESTING |  |
| 4 – 12/29/14 | 12/31/14 | Run Acceptance test on server array |  |
| Phase |  | System Testing at COLO | Status |
| Start Date | Stop Date |  |  |
| 4 – 01/02/15 | 01/10/15 | Swap COMTROL cable and test server array |  |
| 4 – 01/02/15 | 01/10/15 | Simulate loss of internet connection |  |
| 4 – 01/02/15 | 01/10/15 | Simulate Power fail on 1 PDU |  |
| 4 – 01/02/15 | 01/10/15 | Simulate Power fail on both PDU’s |  |
| 5 - 01/10/15 | 01/10/15 | Download test scenario and run a complete platform test. |  |
| 5 – 01/11/15 | 01/11/15 | Sign off on acceptance testing |  |